## Organized by Commenter
Number | Page | Section | Source | Comment | Response
1 | 1 | Summary of Alignment Segments | George Janek - USACE | Under the Section titled "Summary of Alignment Segments", last sentence: you may want to change the word "difference" to different. | This typo has been corrected.
2 | 5 & 6 | Segments 10 - 13 | George Janek - USACE | First and maybe most important from the Corps' standpoint, segments 10, 12, 11, and 13 all have the potential to impact the Corps' Craney Island Dredged Material Management Area (CIDMMA) and/or the Corps' operations there. In the past, the Corps has submitted comments on those impacts and the 408 process that will evaluate those potential impacts. | The previous letter from USACE has been shared with and reviewed by the study team. The comments regarding the CIDMMA will be taken into consideration during the alternative development process for the RCS. It is understood per the June 29, 2016 letter that a Section 408 determination could not be made based on the information from the SEIS at the time.
3 | 5 | I-664 Connector | George Janek - USACE | There may have been design issues with the bridge with 100 foot clearance across the 800-foot wide channel that would have provided "unconstrained navigable access to the CIDMMA" in segment 11. This unrestricted navigable access will have to be considered during the alternatives analysis. | The unrestricted navigable access to CIDMMA will be a major consideration in the alternative development for this study. The design considerations from the SEIS for the I-664 Connector will be reviewed by the study team in the course of alternative development for the RCS.
4 | N/A | General Comment | George Janek - USACE | From the HRCS study, these alternatives were broken up into operationally independent segments that would be advanced as highway funds became available. From a permitting standpoint, each project must be the Least Environmentally Damaging Practicable Alternative (LEDPA) and it must have independent utility. | As alternative development for the RCS progresses, each alternative and any segments that may comprise an alternative will consider independent utility and the LEDPA.
5 | N/A | General Comment | George Janek - USACE | For segments in which transit lanes or improvements are proposed, please provide documentation if those transit lanes are eliminated during the alternatives review process. | At this time, no alternatives or variation of alternatives of mandated segments have been eliminated. Elimination of alternatives and / or any variation of alternatives will be up to the RCS Working Group and documented by the study team.
6 | 1 | Summary of Alignment Segments | Rob Case - HRTPO | “difference combinations” is apparently a typo. | This typo has been corrected.
7 | 4 | Segment 5: I-664 from Terminal Avenue Interchange to I-664 Connector | Rob Case - HRTPO | Segment 5: Please indicate which of the two configurations you’re moving ahead with. | At this time, no alternatives or variation of alternatives of mandated segments have been eliminated. Elimination of alternatives and / or any variation of alternatives will be up to the RCS Working Group and documented by the study team.
8 | 4 | Segment 6: Terminal Avenue Interchange | Rob Case - HRTPO | Segment 6: Same as Segment 5.
9 | 4 | Segment 7: I-664 from I-64 to Terminal Avenue Interchange | Rob Case - HRTPO | Segment 7: Same as Segment 5.
10 | 5 | I-564 and I-564 Connector (2016 HRCS SEIS Segment 10) | Rob Case - HRTPO | Segment 10: Same as Segment 5.
11 | 5 | I-664 Connector including I-664 Interchange (2016 HRCS SEIS Segment 11) | Rob Case - HRTPO | Segment 11: Same as Segment 5.
12 | 6 | I-564 Connector, I-664 Connector, and VA 164 Connector Interchange (2016 HRCS SEIS Segment 12) | Rob Case - HRTPO | Segment 12: Same as Segment 5.
13 | 6 | VA 164 Connector (2016 HRCS Segment 13) | James Wright - City of Portsmouth | Additional coordination will be needed with USACE, USCG, US Navy, the Virginia Port Authority and the City of Portsmouth. As a reminder, the City of Portsmouth must be included since our landfill is located on Craney Island. | It is understood by the study team that coordination with parties affected by any alternative in this study is important. The study team will engage the necessary parties at the appropriate times as the alternative development process moves forward.
14 | 6 | VA 164 Connector (2016 HRCS Segment 13) | James Wright - City of Portsmouth | In the summary, “the proposed terminal expansion is not expected to open in the not too distant future.” The proposed expansion date continues to move past 2050. At out last update, it was out to 2065. | We will revise the summary to reflect the more specific time frame.
15 | 6 | VA 164 Connector (2016 HRCS Segment 13) | James Wright - City of Portsmouth | The layout in the SEIS did not consider the proximity of these interchanges to each other or the overall level of service on VA 164 with existing and proposed conditions | The study team has noted this concern and these items can be considered in the alternative development and evaluation for this study.
16 | 6 | VA 164 Connector (2016 HRCS Segment 13) | James Wright - City of Portsmouth | Any modification to the VIG Interchange will require that the impacts (ability of EMS to respond) to the West Norfolk Road neighborhood, created when it was built, be corrected. This may involve additional work on Wild Duck Lane and on Wyatt Drive. | Impacts of the proposed alternatives will be reviewed and discussed with the necessary stakeholders as alternative development for the RCS progresses.
17 | 6 | VA 164 (2016 HRCS Segment 14) | James Wright - City of Portsmouth | The expansion should not end at College Drive. It should extend to Route 17. | Modifications to alternative segments will be reviewed and considered as the alternatives development progresses. Changes to the alternatives from the SEIS for VA 164 would need to be approved by the RCS Working Group as it is a mandated segment from the SEIS.
18 | 6 | VA 164 (2016 HRCS Segment 14) | James Wright - City of Portsmouth | There is not enough space to widen VA164 into the median to meet both VDOT and VDRPT safety standards and to provide stormwater management. Expansion outside of the existing right of way to accommodate the new lanes and stormwater management impact neighborhoods, and social justice must be addressed. | The design features of the mandated segments are to be reviewed as a part of the alternatives development for this study.
19 | 3 | 2016 HRCS SEIS Segment 2: I-664 from VA 164 to US 58 (Bowers Hill) | Brian Fowler - City of Norfolk | On Page 3 Segment 2 seems mislabeled. | The labeling for Segment 2 was reviewed and is correct and consistent with the 2016 SEIS.
20 | 6 | VA 164 Connector (2016 HRCS Segment 13) | Brian Fowler - City of Norfolk | CIDMMA eastward expansion does not happen along its entire eastern shore. Previously assumed ROW along the entire eastward side of CIDMMA may no longer be valid. | The summary does not suggest the expansion of the CIDMMA extends the entire eastern shore. The expansion plans will be reviewed as a part of the alternatives development and evaluation process.
21 | 6 | VA 164 Connector (2016 HRCS Segment 13) | Brian Fowler - City of Norfolk | During the course of the study I seem to recall discussion as to feasibility issues with construction on the dike or other fill and whether the entire segment would need to be on structure? | Feasibility issues regarding construction of VA 164 Connector on the dike or other fill material are not referenced in the 2016 SEIS Alternatives Technical Report. However, the study team recognizes this potential challenge and the need for consideration in the alternatives development and evaluation process.
22 | 6 | VA 164 Connector (2016 HRCS Segment 13) | Brian Fowler - City of Norfolk | It is incorrect to say that the segment has been designed to accommodate two future interchanges. The horizontal design may accommodate them from a ramp tie-in perspective but to my knowledge true feasibility of interchange design was never established and there appears to be major challenges. | The summary text has been revised to note the 2016 SEIS stated this segment was designed to accommodate the two interchanges identified in the 2006 USACE Feasibility Study for the CIDMMA expansion. The study team acknowledges the concern regarding these interchanges and the concerns will be taken into consideration during the development and evaluation process.
23 | 6 | VA 164 Connector (2016 HRCS Segment 13) | Brian Fowler - City of Norfolk | The design may not address compatibility with the rail line access necessary for the port. | The concern regarding compatibility with the rail line access for the port is acknowledged and will be taken into consideration as the study moves forward.
24 | 6 | VA 164 Connector (2016 HRCS Segment 13) | Brian Fowler - City of Norfolk | Even when the SEIS was conducted, it was not fair to say that the proposed Craney Island Marine Terminal would be expected to open in the “not too distant future”. | The timeline for opening of the Craney Island Marine Terminal has been updated to 2065.
25 | 6 | VA 164 Connector (2016 HRCS Segment 13) | Brian Fowler - City of Norfolk | There are extensive wetland impacts. | The wetland impacts are currently being reviewed by the study team for the mandated segments and will be a consideration in the evaluation process for non-mandated alternatives.
26 | 6 | VA 164 Connector (2016 HRCS Segment 13) | Brian Fowler - City of Norfolk | There is no mention of the segment’s relationship and challenges associated with the Portsmouth Landfill. | The 2016 SEIS made no mention of this segment's relationship with the Portsmouth Landfill. This segement's relationship with the Portsmouth Landfill will be considered as a part of this study's evaluation of the segment.
27 | 6 | VA 164 Connector (2016 HRCS Segment 13) | Brian Fowler - City of Norfolk | The required modifications to 164 from Cedar Lane to W. Norfolk Road, inclusive of the VIG interchange, include in addition to collector-distributor roads and ramp reconfigurations, but realignment/reconstruction of the mainline as well. | Reconstruction of the VA 164 interchange is noted in the summary; however, the realignment of eastbound VA 164 will be added.
28 | 5 | I-564 and I-564 Connector (2016 HRCS SEIS Segment 10) | Brian Fowler - City of Norfolk | While it is correct to say that the SEIS assumed access to from this segment via a SPUI interchange located between NIT and NSN, this concept was actually out of date when the study started. Therefore this information can be very misleading. Ramps to/from the west to this point were determined to be infeasible and other plans were made, including construction of NSN’s Gate 6 which is incompatible with such a design. Instead plans have been developed for the “Air Terminal Interchange” to the east of Hampton Boulevard which would provide connectivity between the west and these facilities, in addition to Hampton Boulevard. These plans must be incorporated into this study’s planning for this segment. | The summary text has been revised to give an indication the SPUI was a proposal of the 2016 SEIS. The connection of this segment to the Intermodal Connector and impacts of the Air Terminal Interchange will be reviewed and considered as a part of the alternative development and evaluation process for this study.

## Organized by Segment Order
Number | Page | Section | Source | Comment | Response
1 | N/A | General Comment | George Janek - USACE | From the HRCS study, these alternatives were broken up into operationally independent segments that would be advanced as highway funds became available. From a permitting standpoint, each project must be the Least Environmentally Damaging Practicable Alternative (LEDPA) and it must have independent utility. | As alternative development for the RCS progresses, each alternative and any segments that may comprise an alternative will consider independent utility and the LEDPA.
2 | N/A | General Comment | George Janek - USACE | For segments in which transit lanes or improvements are proposed, please provide documentation if those transit lanes are eliminated during the alternatives review process. | At this time, no alternatives or variation of alternatives of mandated segments have been eliminated. Elimination of alternatives and / or any variation of alternatives will be up to the RCS Working Group and documented by the study team.
3 | 1 | Summary of Alignment Segments | George Janek - USACE | Under the Section titled "Summary of Alignment Segments", last sentence: you may want to change the word "difference" to different. | This typo has been corrected.
4 | 1 | Summary of Alignment Segments | Rob Case - HRTPO | “difference combinations” is apparently a typo. | This typo has been corrected.
5 | 3 | 2016 HRCS SEIS Segment 2: I-664 from VA 164 to US 58 (Bowers Hill) | Brian Fowler - City of Norfolk | On Page 3 Segment 2 seems mislabeled. | The labeling for Segment 2 was reviewed and is correct and consistent with the 2016 SEIS.
6 | 4 | Segment 5: I-664 from Terminal Avenue Interchange to I-664 Connector | Rob Case - HRTPO | Segment 5: Please indicate which of the two configurations you’re moving ahead with. | At this time, no alternatives or variation of alternatives of mandated segments have been eliminated. Elimination of alternatives and / or any variation of alternatives will be up to the RCS Working Group and documented by the study team.
7 | 4 | Segment 6: Terminal Avenue Interchange | Rob Case - HRTPO | Segment 6: Same as Segment 5.
8 | 4 | Segment 7: I-664 from I-64 to Terminal Avenue Interchange | Rob Case - HRTPO | Segment 7: Same as Segment 5.
11 | 5 & 6 | Segments 10 - 13 | George Janek - USACE | First and maybe most important from the Corps' standpoint, segments 10, 12, 11, and 13 all have the potential to impact the Corps' Craney Island Dredged Material Management Area (CIDMMA) and/or the Corps' operations there. In the past, the Corps has submitted comments on those impacts and the 408 process that will evaluate those potential impacts. | The previous letter from USACE has been shared with and reviewed by the study team. The comments regarding the CIDMMA will be taken into consideration during the alternative development process for the RCS. It is understood per the June 29, 2016 letter that a Section 408 determination could not be made based on the information from the SEIS at the time.
9 | 5 | I-564 and I-564 Connector (2016 HRCS SEIS Segment 10) | Rob Case - HRTPO | Segment 10: Same as Segment 5. Please indicate which of the two configurations you’re moving ahead with. | At this time, no alternatives or variation of alternatives of mandated segments have been eliminated. Elimination of alternatives and / or any variation of alternatives will be up to the RCS Working Group and documented by the study team.
10 | 5 | I-564 and I-564 Connector (2016 HRCS SEIS Segment 10) | Brian Fowler - City of Norfolk | While it is correct to say that the SEIS assumed access to from this segment via a SPUI interchange located between NIT and NSN, this concept was actually out of date when the study started. Therefore this information can be very misleading. Ramps to/from the west to this point were determined to be infeasible and other plans were made, including construction of NSN’s Gate 6 which is incompatible with such a design. Instead plans have been developed for the “Air Terminal Interchange” to the east of Hampton Boulevard which would provide connectivity between the west and these facilities, in addition to Hampton Boulevard. These plans must be incorporated into this study’s planning for this segment. | The summary text has been revised to give an indication the SPUI was a proposal of the 2016 SEIS. The connection of this segment to the Intermodal Connector and impacts of the Air Terminal Interchange will be reviewed and considered as a part of the alternative development and evaluation process for this study.
12 | 5 | I-664 Connector including I-664 Interchange (2016 HRCS SEIS Segment 11) | George Janek - USACE | There may have been design issues with the bridge with 100 foot clearance across the 800-foot wide channel that would have provided "unconstrained navigable access to the CIDMMA" in segment 11. This unrestricted navigable access will have to be considered during the alternatives analysis. | The unrestricted navigable access to CIDMMA will be a major consideration in the alternative development for this study. The design considerations from the SEIS for the I-664 Connector will be reviewed by the study team in the course of alternative development for the RCS.
13 | 5 | I-664 Connector including I-664 Interchange (2016 HRCS SEIS Segment 11) | Rob Case - HRTPO | Segment 11: Same as Segment 5. Please indicate which of the two configurations you’re moving ahead with. | At this time, no alternatives or variation of alternatives of mandated segments have been eliminated. Elimination of alternatives and / or any variation of alternatives will be up to the RCS Working Group and documented by the study team.
14 | 6 | I-564 Connector, I-664 Connector, and VA 164 Connector Interchange (2016 HRCS SEIS Segment 12) | Rob Case - HRTPO | Segment 12: Same as Segment 5. Please indicate which of the two configurations you’re moving ahead with.
15 | 6 | VA 164 Connector (2016 HRCS Segment 13) | James Wright - City of Portsmouth | Additional coordination will be needed with USACE, USCG, US Navy, the Virginia Port Authority and the City of Portsmouth. As a reminder, the City of Portsmouth must be included since our landfill is located on Craney Island. | It is understood by the study team that coordination with parties affected by any alternative in this study is important. The study team will engage the necessary parties at the appropriate times as the alternative development process moves forward.
16 | 6 | VA 164 Connector (2016 HRCS Segment 13) | James Wright - City of Portsmouth | In the summary, “the proposed terminal expansion is not expected to open in the not too distant future.” The proposed expansion date continues to move past 2050. At out last update, it was out to 2065. | We will revise the summary to reflect the more specific time frame.
17 | 6 | VA 164 Connector (2016 HRCS Segment 13) | James Wright - City of Portsmouth | The layout in the SEIS did not consider the proximity of these interchanges to each other or the overall level of service on VA 164 with existing and proposed conditions | The study team has noted this concern and these items can be considered in the alternative development and evaluation for this study.
18 | 6 | VA 164 Connector (2016 HRCS Segment 13) | James Wright - City of Portsmouth | Any modification to the VIG Interchange will require that the impacts (ability of EMS to respond) to the West Norfolk Road neighborhood, created when it was built, be corrected. This may involve additional work on Wild Duck Lane and on Wyatt Drive. | Impacts of the proposed alternatives will be reviewed and discussed with the necessary stakeholders as alternative development for the RCS progresses.
19 | 6 | VA 164 Connector (2016 HRCS Segment 13) | Brian Fowler - City of Norfolk | CIDMMA eastward expansion does not happen along its entire eastern shore. Previously assumed ROW along the entire eastward side of CIDMMA may no longer be valid. | The summary does not suggesting the expansion of the CIDMMA extends the entire eastern shore. The expansion plans will be reviewed as a part of the alternatives development and evaluation process.
20 | 6 | VA 164 Connector (2016 HRCS Segment 13) | Brian Fowler - City of Norfolk | During the course of the study I seem to recall discussion as to feasibility issues with construction on the dike or other fill and whether the entire segment would need to be on structure? | Feasibility issues regarding construction of VA 164 Connector on the dike or other fill material are not referenced in the 2016 SEIS Alternatives Technical Report. However, the study team recognizes this potential challenge and the need for consideration in the alternatives development and evaluation process.
21 | 6 | VA 164 Connector (2016 HRCS Segment 13) | Brian Fowler - City of Norfolk | It is incorrect to say that the segment has been designed to accommodate two future interchanges. The horizontal design may accommodate them from a ramp tie-in perspective but to my knowledge true feasibility of interchange design was never established and there appears to be major challenges. | The summary text has been revised to note the 2016 SEIS stated this segment was designed to accommodate the two interchanges identified in the 2006 USACE Feasibility Study for the CIDMMA expansion. The study team acknowledges the concern regarding these interchanges and the concerns will be taken into consideration during the development and evaluation process.
22 | 6 | VA 164 Connector (2016 HRCS Segment 13) | Brian Fowler - City of Norfolk | The design may not address compatibility with the rail line access necessary for the port. | The concern regrading compatibility with the rail line access for the port is acknowledge and will be taken into consideration as the study moves forward.
23 | 6 | VA 164 Connector (2016 HRCS Segment 13) | Brian Fowler - City of Norfolk | Even when the SEIS was conducted, it was not fair to say that the proposed Craney Island Marine Terminal would be expected to open in the “not too distant future”. | The timeline for opening of the Craney Island Marine Terminal has been updated to 2065.
24 | 6 | VA 164 Connector (2016 HRCS Segment 13) | Brian Fowler - City of Norfolk | There are extensive wetland impacts. | The wetland impacts are currently being reviewed by the study team for the mandated segments and will be a consideration in the evaluation process for non-mandated alternatives.
25 | 6 | VA 164 Connector (2016 HRCS Segment 13) | Brian Fowler - City of Norfolk | There is no mention of the segment’s relationship and challenges associated with the Portsmouth Landfill. | The 2016 SEIS made no mention of this segment's relationship with the Portsmoth Landfill. This segement's relationship with the Portsmouth Landfill can be considered as a part of this study's evaluation of the segement.
26 | 6 | VA 164 Connector (2016 HRCS Segment 13) | Brian Fowler - City of Norfolk | The required modifications to 164 from Cedar Lane to W. Norfolk Road, inclusive of the VIG interchange, include in addition to collector-distributor roads and ramp reconfigurations, but realignment/reconstruction of the mainline as well. | Reconstruction of the VA 164 interchange is noted in the summary; however, the realignment of eastbound VA 164 will be added.
27 | 6 | VA 164 (2016 HRCS Segment 14) | James Wright - City of Portsmouth | The expansion should not end at College Drive. It should extend to Route 17. | Modifications to alternative segments will be reviewed and considered as the alternatives development progresses. Changes to the alternatives from the SEIS for VA 164 would need to be approved by the RCS Working Group as it is a mandated segment from the SEIS.
28 | 6 | VA 164 (2016 HRCS Segment 14) | James Wright - City of Portsmouth | There is not enough space to widen VA164 into the median to meet both VDOT and VDRPT safety standards and to provide stormwater management. Expansion outside of the existing right of way to accommodate the new lanes and stormwater management impact neighborhoods, and social justice must be addressed. | The design features of the mandated segments are to be reviewed as a part of the alternatives development for this study.