{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["RSTPAlloc"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":1,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"RSTPAlloc","index":0,"n_rows":76,"n_cols":65,"rows_kept":76,"cut":false,"hidden":false,"merged":[]}
["Jurisdiction or Agency","UPC Number","Project Name","Year of Project Selection","In Current\nFY 2024-2027\nTIP   ","In Current\nFY 2026-2031\nSYIP ","Active\nProject","FY 2005\n(Federal Share)","FY 2005\n(State Match)","FY 2006\n(Federal Share)","FY 2006\n(State Match)","FY 2007\n(Federal Share","FY 2007\n(State Match)","FY 2008\n(Federal Share)","FY 2008\n(State Match)","FY 2009\n(Federal Share)","FY 2009\n(State Match)","FY 2010\n(Federal Share)","FY 2010\n(State Match)","FY 2011\n(Federal Share)","FY 2011\n(State Match)","FY 2012\n(Federal Share)","FY 2012\n(State Match)","FY 2013\n(Federal Share)","FY 2013\n(State Match)","FY 2014\n(Federal Share)","FY 2014\n(State Match)","FY 2015\n(Federal Share)","FY 2015\n(State Match)","FY 2016\n(Federal Share)","FY 2016\n(State Match)","FY 2017\n(Federal Share)","FY 2017\n(State Match)","FY 2018\n(Federal Share)","FY 2018\n(State Match)","FY 2019\n(Federal Share)","FY 2019\n(State Match)","FY 2020\n(Federal Share)","FY 2020\n(State Match)","FY 2021\n(Federal Share)","FY 2021\n(State Match)","FY 2022\n(Federal Share)","FY 2022\n(State Match)","FY 2023\n(Federal Share)","FY 2023\n(State Match)","FY 2024\n(Federal Share)","FY 2024\n(State Match)","FY 2025\n(Federal Share)","FY 2025\n(State Match)","FY 2026\n(Federal Share)","FY 2026\n(State Match)","FY 2027\n(Federal Share)","FY 2027\n(State Match)","FY 2028\n(Federal Share)","FY 2028\n(State Match)","FY 2029\n(Federal Share)","FY 2029\n(State Match)","FY 2030\n(Federal Share)","FY 2030\n(State Match)","FY 2031\n(Federal Share)","FY 2031\n(State Match)","FY 2032\n(Federal Share)","FY 2032\n(State Match)","Total RSTP Allocations by Project Row"]
["Chesapeake",108954,"Study of Light Rail Extension to Chesapeake",2015,"Yes","Yes","Closing",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1600000,400000,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"SUM(H2:BK2)","v":2000000}]
["Chesapeake","115423","George Washington Highway Widening",2018,"Yes","Yes","Yes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"1200000+400000-800000","v":800000},{"$f":"300000+100000-200000","v":200000},{"$f":"1200000+800000","v":2000000},{"$f":"300000+200000","v":500000},{"$f":"6280000-2704686","v":3575314},{"$f":"1570000-676171","v":893829},8600000,2150000,null,null,null,null,null,null,null,null,{"$f":"SUM(H3:BK3)","v":18719143}]
["Chesapeake",123587,"Route 17/460 Intersection Improvement",2022,"No","Yes","Not yet",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,822752,205688,null,null,1104549,276137,7851322,1962831,12223279]
["Chesapeake",123636,"Military Highway near Bainbridge Boulevard Safety Improvement",2022,"No","Yes","Not yet",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,240000,60000,null,null,93600,23400,1320950,330238,2068188]
["Chesapeake ",123637,"Centerville Turnpike Widening Study",2022,"No","Yes","Not yet",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1301600,325400,1301600,325400,null,null,null,null,3254000]
["Chesapeake",123642,"Pleasant Grove Parkway Alignment Study",2022,"No","Yes","Not yet",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1140000,285000,1140000,285000,null,null,null,null,2850000]
["District-wide",105492,"HRTO Strategic Plan","-----","Yes","Yes","Closing",null,null,null,null,null,null,null,null,null,null,null,null,null,null,320000,80000,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,400000]
["Franklin and Southampton County",118380,"Safety Improvements on Route 258","-----","Yes","Yes","Closing",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"120000+691546","v":811546},{"$f":"30000+172887","v":202887},811546,202887,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2028866]
["Gloucester County",110627,"George Washington Highway (Route 17) Widening - Phase 1",2016,"Yes","VDOT Fredericksburg SYIP","Yes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"1760000-800000","v":960000},{"$f":"440000-200000","v":240000},6400000,{"$f":"1600000","v":1600000},{"$f":"7200000-2065715","v":5134285},{"$f":"1800000-516429","v":1283571},{"$f":"4788212-213626-1932916","v":2641670},{"$f":"1197053-53406-483229","v":660418},{"$f":"4788212+3618233-875690","v":7530755},{"$f":"1197053+904558-218922","v":1882689},{"$f":"3038234-1018700-1438070","v":581464},{"$f":"759558-254675-359517","v":145366},3348591,837148,null,null,{"$f":"3298041+3240000","v":6538041},{"$f":"824510+810000","v":1634510},3807018,951755,46177281]
["Gloucester County","115682","Ware House Road Bike and Pedestrian  Improvements",2018,"Yes","VDOT Fredericksburg SYIP","Closing",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"214400-136519","v":77881},{"$f":"53600-34130","v":19470},null,null,null,null,null,null,null,null,{"$f":"214400-214400","v":0},{"$f":"53600-53600","v":0},null,null,null,null,null,null,null,null,null,null,null,null,null,null,97351]
["Gloucester County",119182,"Route 17 Widening - Short Lane (Route 615) to Main Street (Business 17)",2021,"Yes","VDOT Fredericksburg SYIP","Not yet",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,200000,50000,null,null,null,null,null,null,null,null,null,null,250000]
["Gloucester County","TBD","Gloucester Point Shared Use Path Combined with UPC 110627",2022,"No","Yes","Not yet",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"3348591-3348591","v":0},{"$f":"837148-837148","v":0},null,null,null,null,null,null,0]
["Hampton",97715,"Wythe Creek Road - Widen to 3 Lanes",2010,"Yes","Yes","Yes",11752,2938,301407,75352,null,null,1216562,304141,253910,63477,null,null,{"$f":"240000+12367","v":252367},{"$f":"60000+3092","v":63092},{"$f":"1200000+16505","v":1216505},{"$f":"300000+4126","v":304126},null,null,{"$f":"2400000+3360000-4210601-31879+176024","v":1693544},{"$f":"600000+840000-1052650-7970+44006","v":423386},{"$f":"4866892-1289858-16012-1013988+4723386+220538","v":7490958},{"$f":"1216723-322464-4003-253497+1180847+55134","v":1872740},{"$f":"6653108-3057460-16012-507012","v":3072624},{"$f":"1663277-764365-4003-126753","v":768156},{"$f":"3057460+63903-507012","v":2614351},{"$f":"764365+15976-126753","v":653588},null,null,null,null,{"$f":"5471586+2028012","v":7499598},{"$f":"1367897+507003","v":1874900},{"$f":"5095147+48944","v":5144091},{"$f":"1273787+12236","v":1286023},49775,12444,734650,183663,{"$f":"739631+3396955","v":4136586},{"$f":"184908+849239","v":1034147},4753237,1188309,{"$f":"6591147+381230-1057580","v":5914797},{"$f":"1647787+95307-264395","v":1478699},{"$f":"1120000-709721","v":410279},{"$f":"280000-177430","v":102570},null,null,null,null,null,null,null,null,null,null,58458744]
["HRT","T135","Purchase 44 replacement buses","-----","No","No","Closing",{"$f":"1600000+528000+836000","v":2964000},{"$f":"400000+132000+209000","v":741000},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"SUM(H15:BK15)","v":3705000}]
["HRT","T1824","Replacement of HRT Southside Bus Facility (in the archived tracking tables, this project was under UPC T1795.  There was a UPC T1795, but VDOT stated everything for this project ended up on T1824.","-----","No","No","Closing",278180,69545,null,null,1584340,396085,null,null,4897690,1224422,1882063,470516,1440000,360000,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,12602841]
["HRT","T1821","Peninsula Rapid Transit (formerly Peninsula LRT Project - Prepare EIS)","-----","No","No","Closing",{"$f":"800000+513856","v":1313856},{"$f":"200000+128464","v":328464},{"$f":"2640000-1760000-880000","v":0},{"$f":"660000-440000-220000","v":0},{"$f":"2720000-1520000-1200000","v":0},{"$f":"680000-380000-300000","v":0},null,null,null,null,{"$f":"1200000-640000","v":560000},{"$f":"300000-160000","v":140000},null,null,{"$f":"400000-100000","v":300000},{"$f":"100000-25000","v":75000},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2717320]
["HRT","T7398","Construct Satellite Maintenance Facility at NNWI Airport\nIn the archived tracking tables, this project only had NA as a UPC number - per VDOT, \nproject is T7398.","-----","No","No","Closing",{"$f":"1200000+1200000","v":2400000},{"$f":"300000+300000","v":600000},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3000000]
["HRT","T9093","LRT Extension to Norfolk Naval Station and Virginia Beach Oceanfront (AA/EIS/PE/FD/ROW) \nRegional Fixed Guideway Studies & ROW",2010,"Yes","Yes","Closing",null,null,null,null,null,null,null,null,null,null,null,null,4000000,1000000,{"$f":"4000000-190559","v":3809441},{"$f":"1000000-47640","v":952360},{"$f":"4000000+190559","v":4190559},{"$f":"1000000+47640","v":1047640},{"$f":"5600000-800000","v":4800000},{"$f":"1400000-200000","v":1200000},{"$f":"5600000+800000-69354-1600000-1600000-1600000","v":1530646},{"$f":"1400000+200000-17339-400000-400000-400000","v":382661},null,"   ",null,null,null,null,null,null,null,null,null,null,1600000,400000,4800000,1200000,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,30913307]
["HRT","T11778","Purchase 41 Forty-foot Replacement Buses",2011,"No - Verify with HRT","No","Yes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,46066,11517,null,null,null,null,1600000,400000,null,null,null,null,1051431,262858,439371,109843,193411,48353,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4162850]
["HRT","T14104","goCommute (formerly TRAFFIX)",2011,"Yes","Yes","Yes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,800000,200000,800000,200000,800000,200000,800000,200000,800000,200000,800000,200000,800000,200000,{"$f":"800000-218890","v":581110},{"$f":"200000-54723","v":145277},800000,200000,800000,200000,800000,200000,800000,200000,11726387]
["HRT","T16054","Bus Vehicle Replacement","2014/2015","Yes","Yes","Yes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null," ",null,null,null,null,null,null,null,null,null,7326836,1831709,1945622,486405,{"$f":"40000+640000","v":680000},{"$f":"10000+160000","v":170000},{"$f":"2382030-2382030+1560000","v":1560000},{"$f":"595508-595508+390000","v":390000},{"$f":"4000000+782030-2742150","v":2039880},{"$f":"1000000+195508-685537","v":509971},{"$f":"3164061-2363225","v":800836},{"$f":"791015-590806","v":200209},1562319,390580,{"$f":"11261299-640000","v":10621299},{"$f":"2815325-160000","v":2655325},7634686,1908671,3669566,917392,null,null,null,null,47301306]
["HRT","T17990","Naval Station Norfolk Transit Extension Study FEIS/PE",2015,"No - Verify with HRT","Yes","Yes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4800000,1200000,null,null,null,null,null,null,4800000,1200000,null,null,null,null,null,null,null,null,null,null,null,null,12000000]
["HRT","T19477","Peninsula BRT",2016,"No","No","Delayed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"1636115-1636115","v":0},{"$f":"409029-409029","v":0},{"$f":"4763885-4763885","v":0},{"$f":"1190971-1190971","v":0},null,null,null,null,null,null,null,null,null,null,null,null,3200000,800000,2240000,560000,6800000]
["HRT","T22709","Victoria Boulevard Facility Upgrades - Phase 2",2018,"Yes","Yes","Yes",{"$f":"389294+590000+501000","v":1480294},null,null,null,null,null,510179,127545,null,null,null,null,null,null,50556,12639,160000,40000,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"600777+967560","v":1568337},{"$f":"150194+241890","v":392084},null,null,2800000,700000,{"$f":"1205183-967560","v":237623},{"$f":"301296-241890","v":59406},2600000,650000,null,null,null,null,null,null,null,null,null,null,11388663]
["Isle of Wight County",103021,"Turner Drive and Route 10/32 Intersection Improvements",2011,"Yes","No","Closing","                                   ",null,null,null,null,null,null,null,null,null,null,null,null,null,93658,23415,null,null,null,null,null,null,null,null,null,null,240000,60000,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,417073]
["Isle of Wight County",123641,"Route 17 Widening at Smiths Neck Road",2022,"No","Yes","Not yet",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,947941,236985,654366,163592,null,null,null,null,2002884]
["James City County",17633,"Richmond Road Multi-Use Trail","-----","Yes","Yes","Closing",{"$f":"232000+2465+11519","v":245984},{"$f":"58000+616+2880","v":61496},null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"146020-146020","v":0},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,618130,154533,null,null,116816,29204,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1226163]
["James City County",100200,"Skiffes Creek Connector",2010,"Yes","Yes","Closing",{"$f":"1464000+3960000+2576000","v":8000000},{"$f":"366000+990000+644000","v":2000000},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"8000000-3200000-507012-463636","v":3829352},{"$f":"2000000-800000-126753-115909","v":957338},{"$f":"12000000-6105157-75690","v":5819153},{"$f":"3000000-1526289-18922","v":1454789},{"$f":"9305157-1417790","v":7887367},{"$f":"2326289-354448","v":1971841},{"$f":"2000492+6020390-1061906","v":6958976},{"$f":"500123+1505097-265476","v":1739744},{"$f":"5146758-116816-3395772+3395772-2333856-2696086","v":0},{"$f":"1286689-29204-848930+848930-583464-674021","v":0},{"$f":"1235253+463636-1235253-463636","v":0},{"$f":"308813+115909-308813-115909","v":0},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,40618560]
["James City County",100920,"Croaker Road Widening and Multi-Purpose Trail  ",2011,"Yes","Yes","Yes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,400000,100000,{"$f":"2400000-800000","v":1600000},{"$f":"600000-200000","v":400000},800000,200000,1061906,265476,{"$f":"3395772-3395772+2333856","v":2333856},{"$f":"848930-848930+583464","v":583464},{"$f":"6880000+1756369","v":8636369},{"$f":"1720000+439092","v":2159092},360000,90000,2504578,626145,{"$f":"1600000+1104721","v":2704721},{"$f":"400000+276180","v":676180},null,null,null,null,null,null,null,null,null,null,null,null,25501787]
["James City County",102980,"Route 60 Multi-Modal Corridor Upgrade US Route 60 (Pocahontas Trail) Widening and Complete Street",2011,"Yes","Yes","Yes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"640000-199394+199394-132000","v":508000},{"$f":"160000-49848+49848-33000","v":127000},1040000,260000,null,null,null,null,1476547,369138,{"$f":"1235253-931937+123452","v":426768},{"$f":"308813-232984+30863","v":106692},1636116,409029,{"$f":"3260000-2504578+1120000+731235","v":2606657},{"$f":"815000-626145+280000+182809","v":651664},{"$f":"1248424-1219870","v":28554},{"$f":"312106-304967","v":7139},{"$f":"1904970+3160000","v":5064970},{"$f":"476243+790000","v":1266243},{"$f":"2200000-620467","v":1579533},{"$f":"550000-155117","v":394883},null,null,null,null,null,null,null,null,17958933]
["James City County",111237,"James City County Master Transportation Plan",2016,"Yes","Yes","Delayed",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,40000,10000,{"$f":"360000-360000","v":0},{"$f":"90000-90000","v":0},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,50000]
["Newport News",4483,"Atkinson Boulevard - Construct New Road",2010,"Yes","No","Closing",{"$f":"616800+792","v":617592},{"$f":"154200+198","v":154398},null,null,982408,245602,null,null,null,null,null,null,{"$f":"320000-197301-43835-78864","v":0},{"$f":"80000-49325-10959-19716","v":0},null,null,764701,191175,null,null,null,null,8000000,2000000,{"$f":"24964578-8176098-79915","v":16708565},{"$f":"6241144-2044025-19979","v":4177140},{"$f":"4800000+2694843+79915","v":7574758},{"$f":"1200000+673711+19979","v":1893690},{"$f":"5481255+1809706-1809706","v":5481255},{"$f":"1370314+452426-452426","v":1370314},{"$f":"257872-257872","v":0},{"$f":"64468-64468","v":0},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,50161598]
["Newport News",102734,"Amtrak Multimodal Station Development (PE only)",2010,"Yes","No","Closing",null,null,{"$f":"167749-167749+167749","v":167749},{"$f":"41937-41937+41937","v":41937},null,null,null,null,null,null,null,null,{"$f":"800000+29297-829297+829297+197301-1005910+1005910-685680-320230","v":20688},{"$f":"200000+7324-207324+207324+49325-251477+251477-171420-80057","v":5172},{"$f":"800000-800000+602954-602954+602954-602954","v":0},{"$f":"200000-200000+150739-150739+150739-150739","v":0},null,null,null,null,null,null,{"$f":"506614-506614","v":0},{"$f":"126654-126654","v":0},{"$f":"278046+2169930-2447976","v":0},{"$f":"69511+542483-611994","v":0},{"$f":"656966-656966","v":0},{"$f":"164241-164241","v":0},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,235546]
["Newport News",109075,"Amtrak Multimodal Station - Site Grading and Drainage (child project of UPC 102734)","-----","Yes","Yes - because of an issue","Closing",{"$f":"278051+19121+399258-399258+399258","v":696430},{"$f":"69513+4780+99814-99814+77451","v":151744},19035,4759,61707,15427,null,null,null,null,null,null,43835,{"$f":"10959+22362","v":33321},null,null,null,null,null,null,null,null,null,null,null,1,null,null,1809706,452426,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,3288391]
["Newport News",109076,"Amtrak Multimodal Station - Station, Platform, and Parking Lot (child project of UPC 102734)","-----","Yes","Yes","Closing",{"$f":"309527-309527+231475-231475","v":0},{"$f":"77382-77382+57869-57869","v":0},{"$f":"167749-167749","v":0},{"$f":"41937-41937","v":0},null,null,null,null,null,null,null,null,{"$f":"829297-829297+78864+1005910-1005910+685680","v":764544},{"$f":"207324-207324+19716+251477-251477+171420","v":191136},{"$f":"800000+602954-602954","v":800000},{"$f":"200000+150739-150739","v":200000},null,null,null,null,null,null,506614,126654,2447976,611994,656966,164241,null,null,257872,64468,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,6792465]
["Newport News",123764,"Birthplace of America Trail (BoAT): \nTrail 757 - Pocahontas Trail at Green Mountain Parkway to Warwick Boulevard at Falls Reach ",2022,"No","Yes","Not yet",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1838400,459600,6064000,1516000,null,null,null,null,9878000]
["Norfolk",84243,"Military Highway Widening - Phase I",2010,"Yes","No","Closing",null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"800000-800000","v":0},{"$f":"200000-200000","v":0},{"$f":"1600000+800000","v":2400000},{"$f":"400000+200000","v":600000},1600000,400000,2154752,538688,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,7693440]
["Norfolk",107039,"Campostella Bridge Rehabilitation",2014,"Yes","Yes","Closing",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,4800000,1200000,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,6000000]
["Norfolk","115379","Newtown Road Corridor Study",2018,"Yes","Yes","Closing",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,200000,50000,null,null,null,null,null,null,null,null,null,null,null,null,null,null,250000]
["Norfolk","115424","Southside Bike Network",2018,"Yes","Yes","Yes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,83200,20800,729520,182380,null,null,null,null,null,null,null,null,null,null,null,null,1015900]
["Norfolk",119276,"Brambleton Avenue Bridge Rehabilitation",2020,"Yes","Yes","Yes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2400000,600000,800000,200000,null,null,null,null,null,null,null,null,4000000]
["Norfolk",123588,"Citywide Fiber Upgrades",2022,"No","Yes","Not yet",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,184560,46140,1427184,356796,1365680,341420,1365680,341420,5428880]
["Norfolk",123635,"Military Highway at Poplar Hall Drive Shared Use Path",2022,"No","Yes","Not yet",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,359062,89766,1503704,375926,1653580,413395,2162518,540630,7098581]
["Norfolk",123638,"Downtown Norfolk/Market Street/St. Paul's Comprehensive Study",2022,"No","Yes","Not yet",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1000000,250000,1000000,250000,null,null,null,null,2500000]
["Poquoson",13427,"Wythe Creek Road Widening - Phase I",2010,"Yes","Yes","Yes",{"$f":"204800+117600+702400+702400","v":1727200},{"$f":"51200+29400+175600+175600","v":431800},null,null,800000,200000,800000,200000,null,null,null,null,160000,40000,320000,80000,1316680,329170,1166630,291658,{"$f":"6636690-1836690-4723386","v":76614},{"$f":"1659172-459172-1180847","v":19153},null,null,1836690,459172,null,null,null,null,null,null,496000,124000,null,null,null,null,1183045,295761,686763,171691,{"$f":"686763+1057580","v":1744343},{"$f":"171691+264395","v":436086},null,null,null,null,null,null,null,null,null,null,null,null,15392456]
["Port of Virginia",109409,"Port of Virginia ITS Master Plan for Hampton Roads",2015,"Yes","Yes","Closing",{"$f":"160000-160000+8777+32207+6286+32605+79658","v":159533},{"$f":"40000-40000+1585+8052+1571+8151+19914","v":39273},null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"467","v":467},null,null,null,null,null,null,null,null,null,610,null,null,null,null,null,null,null,null,null,{"$f":"150000-131814","v":18186},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,218069]
["Portsmouth",107035,"George Washington Highway Corridor Improvements, including Elm Street Intersection",2014,"Yes","Yes","Yes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,440000,110000,null,null,1200000,300000,{"$f":"3120000-1267387","v":1852613},{"$f":"780000-316847","v":463153},null,null,827387,206847,null,null,null,null,null,null,null,null,null,null,null,null,5400000]
["Suffolk","69050","Bridge Road/Shoulders Hill Road Intersection Improvements",2018,"Yes","Yes","Yes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"3600000-176607-731235-1201258-782030","v":708870},{"$f":"900000-44152-182809-300315-195508","v":177216},{"$f":"3260000-800000-827387-1104721-381230","v":146662},{"$f":"815000-200000-206847-276180-95307","v":36666},null,null,null,null,null,null,null,null,null,null,null,null,1069414]
["Suffolk",102994,"Intelligent Transportation Systems (ITS) Upgrades",2011,"Yes","Yes","Closing",{"$f":"293847-293487+293487","v":293847},{"$f":"73462-73462+73462","v":73462},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"108000+199394-199394+132000","v":240000},{"$f":"27000+49848-49848+33000","v":60000},{"$f":"1212000-201038-56000","v":954962},{"$f":"303000-50260-14000","v":238740},null,null,{"$f":"124000-124000","v":0},{"$f":"31000-31000","v":0},null,null,null,null,null,null,null,null,null,null," ",null,null,null,null,null,null,null,null,null,null,null,1861011]
["Suffolk",107057,"West End Suffolk Bypass Interchange IMR study",2014,"Yes","No","Closing",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"160000-124000-949","v":35051},{"$f":"40000-31000-237","v":8763},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,43814]
["Suffolk",108984,"Speights Spillway Bridge Replacement",2015,"Yes","Yes","Yes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,201038,50260,null,null,124000,31000,1080000,270000,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1756298]
["Suffolk",111036,"Suffolk Bypass / Godwin Boulevard - Wilroy Road - Pruden Boulevard IMR",2016,"Yes","Yes","Yes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,56000,14000,null,null,949,237,null,null,{"$f":"40000-40000","v":0},{"$f":"10000-10000","v":0},{"$f":"1560000-1560000","v":0},{"$f":"390000-390000","v":0},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,71186]
["Suffolk Transit","115421","Suffolk Transit Operations Facility",2018,"Yes","Yes","Yes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,48000,12000,1464053,366013,null,null,null,null,null,null,null,null,null,null,null,null,1890066]
["Suffolk",123765,"Citywide Traffic Signal System Timing",2022,"No","Yes","Not yet",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,392000,98000,260000,65000,76000,19000,null,null,910000]
["Virginia Beach",15828,"Elbow Road - Phase II-B",2015,"Yes","Yes","Yes",{"$f":"74+121474+380445+541002","v":1042995},{"$f":"19+30369+95111+135251","v":260750},701561,175390,{"$f":"668090-668090+668090","v":668090},{"$f":"167022-167022+153497","v":153497},9251,2313,604591,151148,183926,45982,3767,942,{"$f":"377698+400000-400000+5061+252056-252056+240000+26","v":622785},{"$f":"94424+100000-100000+1265+63014-63014+60000+6","v":155695},null,null,null,null,null,null,null,null,{"$f":"173750-173750+185059","v":185059},{"$f":"43437-43437+45654","v":45654},null,null,3033246,758312,{"$f":"5485943+212101","v":5698044},{"$f":"1371486+53025","v":1424511},null,null,{"$f":"10890236-10890236+1858400","v":1858400},{"$f":"2722559-2722559+464600","v":464600},{"$f":"8977074-8577074-400000+1901600+88323","v":1989923},{"$f":"2244268-2144268-100000+475400+22081","v":497481},{"$f":"7265386-7265386+1305380","v":1305380},{"$f":"1816346-1816346+326345","v":326345},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,22369638]
["Virginia Beach",17630,"Witchduck Road/I-264 Interchange Improvement - PE and RW Only","-----","Yes","Yes","Closing",{"$f":"400000+320000+200000+20000+80000+200000+400000+272000","v":1892000},{"$f":"100000+80000+50000+5000+20000+50000+100000+68000","v":473000},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2365000]
["Virginia Beach",103004,"Regional Signal Preemption Program",2011,"Yes","Yes","Closing",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,106400,26600,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,133000]
["Virginia Beach",103005,"Centerville Turnpike Widening from Kempsville Road to Indian River Road",2011,"Yes","Yes","Yes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"5698746-2498746-95927-7726","v":3096347},{"$f":"1424687-624687-23982-1932","v":774086},{"$f":"4701254-800000-16012","v":3885242},{"$f":"1175313-200000-4003","v":971310},3410686,852671,null,null,{"$f":"1520000-1520000","v":0},{"$f":"380000-380000","v":0},28555,7139,{"$f":"7265386+1680000+2167523+1940712","v":13053621},{"$f":"1816346+420000+541881+485178","v":3263405},{"$f":"4000000+1600000-2196078+421855","v":3825777},{"$f":"1000000+400000-549020+105464","v":956444},null,null,null,null,null,null,null,null,null,null,null,null,null,null,34125283]
["Virginia Beach",107064,"Bus Stop Infrastructure and Accessibility Improvements - Phase 9",2014,"Yes","Yes","Yes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,319175,79794,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,398969]
["Virginia Beach",112317,"Elbow Road Extended - Phase II-C (child project of UPC 15828)","N/A\nchild project","Yes","Yes","Yes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,400000,100000,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"10890236-800000+1200000","v":11290236},{"$f":"2722559-200000+300000","v":2822559},{"$f":"8577074-2349670+1200000","v":7427404},{"$f":"2144268-587417+300000","v":1856851},null,null,1201258,300315,null,null,null,null," ",null,null,null,null,null,null,null,null,null,25398623," "]
["Virginia Beach",112318,"Elbow Road Extended - Phase II-D (child project of UPC 15828)","N/A\nchild project","Yes","Yes","Yes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,400000,100000,{"$f":"7265386-7265386","v":0},{"$f":"1816346-1816346","v":0},{"$f":"4000000-4000000","v":0},{"$f":"1000000-1000000","v":0},{"$f":"2400000-1248424","v":1151576},{"$f":"600000-312106","v":287894},null,null,null,null,null,null,null,null,null,null,null,null,1939470]
["Virginia Beach",115543,"Nimmo Parkway - Phase VIIB",2020,"Yes","Yes","Yes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"400000-400000","v":0},{"$f":"100000-100000","v":0},{"$f":"4000000-800000","v":3200000},{"$f":"1000000-200000","v":800000},{"$f":"4000000-1807596","v":2192404},{"$f":"1000000-451899","v":548101},3600000,900000,null,null,null,null,2207596,551899,null,null,14000000]
["Virginia Beach",119275,"Laskin Road Phase III",2020,"Yes","Yes","Not yet",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"2935200-353480","v":2581720},{"$f":"733800-88370","v":645430},3521511,880378,3972572,993143,7386620,1846655,{"$f":"7386620+353480","v":7740100},{"$f":"1846655+88370","v":1935025},null,null,31503154]
["Virginia Beach",123585,"Laskin Road Phase I-B",2022,"No","Yes","Not yet",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null," ",null,null,1914288,478572,4455770,1113942,3240000,810000,8950153,2237538,23200263]
["WATA",115425,"Strategic Plan and Comprehensive Operating Analysis Study",2018,"Yes","Yes","Yes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,240000,60000,null,null,null,null,null,null,null,null,null,null,null,null,null,null,300000]
["WATA",119278,"Transit Strategic Plan Major Update",2020,"Yes","Yes","Not yet",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"288000-288000","v":0},{"$f":"72000-72000","v":0},null,null,null,null,null,null,null,null,null,null,{"$f":"SUM(H67:BK67)","v":0}]
["WATA","T1818","Bus on Chassis Vehicles - 5 New Replacement Vehicles","-----","No","No","Closing",156000,39000,104444,26000,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"SUM(H68:BK68)","v":325444}]
["WATA","T11932","WATA Administration and Operations Facility - Phase 1",2011,"Yes","Yes","Yes",{"$f":"54100+400000","v":454100},{"$f":"13525+100000","v":113525},null,null,null,null,null,null,3892,973,null,null,63227,15807,null,null,null,null,null,null,69354,17339,null,null,366601,91650,{"$f":"2960000+856059","v":3816059},{"$f":"740000+214015","v":954015},{"$f":"4240000-1840000+288206","v":2688206},{"$f":"1060000-460000+72052","v":672052},{"$f":"1840000+136519","v":1976519},{"$f":"460000+34130","v":494130},null,null,107036,24447,931937,232984,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"SUM(H69:BK69)","v":13093853}]
["York County",16314,"Penniman Road/Government Road Improvements",2018,"Yes","Yes","Yes",{"$f":"266471+502400","v":768871},{"$f":"66618+125600","v":192218},null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null," ",null,null,null,null,null,null,1261232,315308,null,null,1,0,null,null,null,null,null,null,null,null,null,null,null,null,null,null,{"$f":"SUM(H70:BK70)","v":2537630}]
["York County",111787,"George Washington Memorial Highway (Route 17) Widening ",2020,"Yes","Yes","Yes",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,1200000,300000,840000,210000,3752000,938000,null,null,null,null,null,null,7240000]
["York County",119279,"York County Roadway Needs Assessment",2020,"Yes","Yes","Not yet",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,240000,60000,240000,60000,null,null,null,null,null,null,null,null,600000]
[]
["HRTPO RSTP Reserve Account",70715,"HRTPO RSTP Reserve Account (VDOT's Balance Entry)",null,null,null,null,{"$f":"541002-541002","v":0},{"$f":"135251-135251","v":0},0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"26-26","v":0},{"$f":"6-6","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"212101-212101+136519-136519","v":0},{"$f":"53025-53025+34130-34130","v":0},0,0,{"$f":"1476548-1476548+107036-107036","v":0},{"$f":"369137-369137+24447-24447","v":0},{"$f":"211775-123452+1636115-640000-967560-28555-88323","v":0},{"$f":"52944-30863+409029-160000-241890-7139-22081","v":0},{"$f":"807760+4763885-2167523-1305380-158030-1940712","v":0},{"$f":"201940+1190971-541881-326345-39507-485178","v":0},{"$f":"421855-421855","v":0},{"$f":"105464-105464","v":0},{"$f":"230470-230470","v":0},{"$f":"57617-57617","v":0},{"$f":"748780-748780","v":0},{"$f":"187195-187195","v":0},{"$f":"218890-218890","v":0},{"$f":"54723-54723","v":0},{"$f":"6974454-3348591-1690100","v":1935763},{"$f":"1743614-837148-422525","v":483941},{"$f":"4276988-1723902","v":2553086},{"$f":"1069247-430975","v":638272},{"$f":"4841071","v":4841071},{"$f":"1210268","v":1210268},1165168,291292,{"$f":"SUM(H74:BK74)","v":13118861}]
[]
["Total RSTP Allocated to Projects by FY Column",null,null,null,null,null,null,{"$f":"SUM(H2:H72)","v":24502634},5732613,1294196,323438,4096545,1010611,2535992,633999,5760083,1440020,2625989,656498,6748428,1709470,10379478,2594752,8031940,2007985,9814926,2453732,10767572,2691893,11579238,2894810,24159852,6039199,22330859,5582715,27819725,6954933,28419508,7104877,{"$f":"SUM(AN2:AN72)","v":27506984},6876746,29076474,7262261,31885175,7971294,32287361,8071840,28432506,7108126,29191742,7297937,30357761,7589442,30964917,7741229,29648452,7412113,29662810,7415703,28019146,7004786,28497641,7124412]